## WBS
WBS Code | Task / Subtask | Description | Assigned Dev | Story Points (1 = 1 hour) | Predecessor(s) | Start Date (Planned) | Deadline (Planned) | Date Started (Actual) | Date Finished (Actual) | Status
0.0 | Project Planning & Design |  |  |  | - |  |  |  |  | Completed
0.1 | Requirements Gathering | Finalize must-haves and scope from approved proposal | ALL | 8 | - | 2026-06-18 | 2026-06-19 | 2026-06-23 | 2026-06-24 | Completed
0.2 | Database Schema Design | Design Supabase schema: users, exams, questions, sessions, logs | ALL | 8 | - | 2026-06-19 | 2026-06-20 | 2026-06-24 | 2026-06-25 | Completed
0.3 | UI/UX Wireframes | Wireframes for student desktop and teacher web screens | ALL | 12 | - | 2026-06-20 | 2026-06-23 | 2026-06-25 | 2026-06-29 | Completed
1.0 | System-Wide Exam Lockdown Module (Windows API) |  |  |  | - |  |  |  |  | Completed
1.1 | Low-Level Keyboard Hook Setup | SetWindowsHookEx WH_KEYBOARD_LL foundation | ROBERT | 7 | 0.2 | 2026-06-29 | 2026-06-30 | 2026-07-02 | 2026-07-04 | Completed
1.1.1 | Block Alt+Tab & App-Switching Shortcuts | Intercept and suppress app-switch shortcuts | ROBERT | 1 | 1.1 | 2026-06-30 | 2026-07-01 | 2026-07-03 | 2026-07-04 | Completed
1.1.2 | Block Windows Key & Start Menu | Intercept Windows key and Start menu access | ROBERT | 1 | 1.1.1 | 2026-06-30 | 2026-07-01 | 2026-07-03 | 2026-07-04 | Completed
1.1.3 | Block Task Manager Access | Disable Ctrl+Shift+Esc and Ctrl+Alt+Del handling | ROBERT | 3 | 1.1.2 | 2026-06-30 | 2026-07-01 | 2026-07-03 | 2026-07-04 | Completed
1.1.4 | Block Copy-Paste Shortcuts | Intercept Ctrl+C / Ctrl+V / Ctrl+X | ROBERT | 1 | 1.1.3 | 2026-06-30 | 2026-07-01 | 2026-07-03 | 2026-07-04 | Completed
1.1.5 | Block Screenshot Tools | Intercept PrintScreen and Win+Shift+S | ROBERT | 1 | 1.1.4 | 2026-06-30 | 2026-07-01 | 2026-07-03 | 2026-07-04 | Completed
1.2 | Fullscreen Kiosk Window & Focus Lock | Always-on-top kiosk window captures all input focus | ROBERT | 2 | 1.1.5 | 2026-06-29 | 2026-06-30 | 2026-07-02 | 2026-07-04 | Completed
1.3 | Bypass Logging | Log bypass attempts with timestamp | ROBERT | 2 | 1.2 | 2026-07-30 | 2026-07-31 | 2026-07-18 | 2026-07-19 | Completed
1.4 | Mute Audio on Application Launch | Automatically mutes system audio when the application starts, before the student can access any exam or activity. | STEPHEN | 1 | 1.2 | 2026-07-30 | 2026-07-31 | 2026-07-17 | 2026-07-18 | Completed
1.5 | Lockdown Release on Exam Exit | Lift lockdown once student finishes and leaves the app | ROBERT | 2 | 1.4 | 2026-06-29 | 2026-06-30 | 2026-07-02 | 2026-07-04 | Completed
2.0 | Local Code Compiler & Automated Assessment Engine |  |  |  | - |  |  |  |  | Completed
2.1 | Local GCC Compiler Integration | Wire local GCC into the code execution engine | STEPHEN | 3 | 0.2 | 2026-06-29 | 2026-06-30 | 2026-07-02 | 2026-07-04 | Completed
2.2 | Process-Isolated Code Execution | Isolated runs, configurable time limit, temp file cleanup | STEPHEN | 4 | 2.1 | 2026-06-30 | 2026-07-01 | 2026-07-11 | 2026-07-19 | Completed
2.3 | Hidden Test Case Runner & Output Comparison | Run hidden teacher-defined test cases, compare output | STEPHEN | 4 | 2.2 | 2026-06-30 | 2026-07-01 | 2026-07-11 | 2026-07-19 | Completed
2.4 | Partial Credit Scoring Engine | Pass/fail plus partial credit scoring logic | STEPHEN | 1 | 2.3 | 2026-06-30 | 2026-07-01 | 2026-07-11 | 2026-07-19 | Completed
2.5 | Code Check Attempt Tracking & Deduction | Track check attempts, apply teacher-configured point deduction | STEPHEN | 2 | 2.4 | 2026-06-30 | 2026-07-01 | 2026-07-11 | 2026-07-19 | Completed
3.0 | In-App Code Editor (Student Desktop) |  |  |  | - |  |  |  |  | Completed
3.1 | Monaco Editor Integration | Embed Monaco editor inside the locked kiosk window | STEPHEN | 3 | 0.3 | 2026-06-29 | 2026-06-30 | 2026-07-02 | 2026-07-04 | Completed
3.2 | Run Against Visible Sample Test Cases | Students test code before final submission | STEPHEN | 2 | 3.1 | 2026-06-29 | 2026-06-30 | 2026-07-11 | 2026-07-19 | Completed
4.0 | Exam Join Flow (Exam Code + Verification Code) |  |  |  | - |  |  |  |  | Completed
4.1 | Join by Exam Code (Dashboard) | Student enters class code to enroll in an exam | ROBERT | 2 | 0.2 | 2026-07-01 | 2026-07-02 | 2026-07-05 | 2026-07-06 | Completed
4.2 | Verification Code Entry (Confirmation Screen) | Student enters teacher-set verification code before start | BRIAN | 1 | 4.1 | 2026-07-01 | 2026-07-03 | 2026-07-08 | 2026-07-09 | Completed
4.3 | Server-Side Verification Code RPC | Postgres RPC checks code without exposing it to client | BRIAN | 1 | 4.2 | 2026-07-01 | 2026-07-03 | 2026-07-08 | 2026-07-09 | Completed
4.4 | Session Auto-Invalidation on Exam End | Exam code invalidated once session/exam closes | ROBERT | 1 | 4.3 | 2026-07-01 | 2026-07-02 | 2026-07-05 | 2026-07-06 | Completed
5.0 | Cloud Data Storage & Synchronization |  |  |  | - |  |  |  |  | Completed
5.1 | Supabase Schema Implementation | Exams, questions, sessions, answers, logs tables live in Supabase | STEPHEN | 4 | 0.2 | 2026-07-05 | 2026-07-07 | 2026-07-08 | 2026-07-10 | Completed
5.2 | Real-Time Sync of Progress & Submissions | Live sync of student progress and results to cloud | STEPHEN & ROBERT | 4 | 5.1 | 2026-07-07 | 2026-07-10 | 2026-07-10 | 2026-07-17 | Completed
6.0 | Student Desktop Core Screens |  |  |  | - |  |  |  |  | Completed
6.1 | Login / Logout | Student authentication against Supabase | ROBERT | 1 | 5.1 | 2026-06-24 | 2026-06-25 | 2026-07-01 | 2026-07-02 | Completed
6.2 | Dashboard (Latest Sessions) | Shows latest 3 exam sessions, connected to Supabase | STEPHEN & ROBERT | 3 | 6.1 | 2026-06-24 | 2026-06-25 | 2026-07-01 | 2026-07-11 | Completed
6.3 | Archive (All Sessions) | Paginated, filtered, sorted session history | STEPHEN & ROBERT | 3 | 6.2 | 2026-06-24 | 2026-06-25 | 2026-07-01 | 2026-07-11 | Completed
7.0 | Teacher Monitoring Dashboard |  |  |  | - |  |  |  |  | Completed
7.1 | Login / Logout (Role-Based Redirect) | Teacher/admin authentication with role routing | ROBERT | 1 | 5.1 | 2026-06-24 | 2026-06-25 | 2026-07-01 | 2026-07-02 | Completed
7.2 | Cross-Device Access | Manage exams from any authorized device with internet | BRIAN | 1 | 7.1 | 2026-07-05 | 2026-07-07 | 2026-07-09 | 2026-07-10 | Completed
8.0 | Multi-Type Exam Builder |  |  |  | - |  |  |  |  | Completed
8.1 | Exam Library (Publish / End / Delete) | Manage exam lifecycle and status transitions | BRIAN | 2 | 5.1 | 2026-07-10 | 2026-07-12 | 2026-07-03 | 2026-07-04 | Completed
8.2 | Multiple Choice Question Builder |  | BRIAN | 3 | 8.1 | 2026-07-13 | 2026-07-17 | 2026-07-03 | 2026-07-04 | Completed
8.2.1 | Create Question, Choices, Correct Answer | MCQ authoring with answer choices | BRIAN | 2 | 8.1 | 2026-07-13 | 2026-07-14 | 2026-07-03 | 2026-07-04 | Completed
8.2.2 | Configure Point Values | Per-question point configuration | BRIAN | 1 | 8.2.1 | 2026-07-17 | 2026-07-17 | 2026-07-03 | 2026-07-04 | Completed
8.3 | Coding Question Builder |  | BRIAN | 7 | 8.1 | 2026-07-18 | 2026-07-25 | 2026-07-03 | 2026-07-04 | Completed
8.3.1 | Problem Statement, I/O Specs, Constraints | Author coding question prompt and specs | BRIAN | 2 | 8.1 | 2026-07-18 | 2026-07-19 | 2026-07-03 | 2026-07-04 | Completed
8.3.2 | Visible Sample Test Cases | Student-facing practice test cases | BRIAN | 2 | 8.3.1 | 2026-07-20 | 2026-07-20 | 2026-07-03 | 2026-07-04 | Completed
8.3.3 | Hidden Grading Test Cases | Grading-only test cases never shown to students | BRIAN | 1 | 8.3.2 | 2026-07-21 | 2026-07-21 | 2026-07-03 | 2026-07-04 | Completed
8.3.4 | Time Limit & Scoring Config | Per-question execution time limit and scoring rules | BRIAN | 1 | 8.3.3 | 2026-07-24 | 2026-07-24 | 2026-07-03 | 2026-07-04 | Completed
8.3.5 | Run Code Attempt Penalty Config | Teacher-configurable check-attempt point deduction | BRIAN | 1 | 8.3.4 | 2026-07-25 | 2026-07-25 | 2026-07-03 | 2026-07-04 | Completed
8.4 | Test Case Preview & Validation | Validate test cases before publishing the exam | BRIAN | 3 | 8.3.5 | 2026-07-26 | 2026-07-27 | 2026-07-16 | 2026-07-17 | Completed
9.0 | Admin Dashboard & Audit Logging |  |  |  | - |  |  |  |  | Completed
9.1 | Teacher Account CRUD | Create, view, update, deactivate/delete teacher accounts | STEPHEN | 2 | 0.2 | 2026-06-20 | 2026-06-22 | 2026-06-29 | 2026-07-04 | Completed
9.2 | Audit Log Recording | Logs create/update/delete/reset/access actions | STEPHEN | 1 | 9.1 | 2026-06-22 | 2026-06-24 | 2026-06-30 | 2026-07-01 | Completed
9.3 | Audit Log Review Screen | Search and filter administrative action history | STEPHEN | 1 | 9.2 | 2026-06-22 | 2026-06-24 | 2026-06-30 | 2026-07-01 | Completed
12.0 | Nice-to-Have Features |  |  |  | - |  |  |  |  | Completed
12.3 | Question Bank & Reusability | Save, browse, search, and reuse questions across exams | BRIAN | 3 | 8.4 | 2026-08-28 | 2026-08-31 | 2026-07-06 | 2026-07-08 | Completed
M1 | 50% MILESTONE DEFENSE | Group milestone checkpoint, not an individual task | ALL |  | - | 2026-06-18 | 2026-07-23 |  |  | Not Started
1.0 | System-Wide Exam Lockdown Module (Windows API) |  |  |  | - |  |  |  |  | Not Started
1.6 | Active Process Monitoring | Detect disallowed apps | ROBERT |  | 1.2 | 2026-07-30 | 2026-07-31 |  |  | Not Started
1.7 | Keystroke Logging | Timestamped keystroke logs tied to question interactions | ROBERT |  | 1.3 | 2026-08-03 | 2026-08-04 |  |  | Not Started
1.8 | Auto-Close Background Apps | Runs automatically on application launch | ROBERT |  | 1.3 | 2026-08-05 | 2026-08-05 |  |  | Not Started
5.0 | Cloud Data Storage & Synchronization |  |  |  | - |  |  |  |  | Not Started
5.3 | Offline Fallback / Sync Queue | Local SQLite queue syncs once connection returns | STEPHEN |  | 5.2 | 2026-08-01 | 2026-08-02 |  |  | Not Started
7.0 | Teacher Monitoring Dashboard |  |  |  | - |  |  |  |  | Not Started
7.3 | Live View: Students, Question, Progress | Real-time visibility into all connected students | STEPHEN |  | 7.1 | 2026-07-30 | 2026-07-31 |  |  | Not Started
7.4 | End Session / Remove Student Controls | Teacher can end exam or remove a specific student | ROBERT |  | 7.3 | 2026-07-30 | 2026-07-31 |  |  | Not Started
7.5 | Violation Alerts (Name, Type, Timestamp) | Instant alert display on the monitoring dashboard | TBD |  | 7.3 | 2026-08-06 | 2026-08-10 |  |  | Not Started
7.6 | Student Movement Tracker | Logs question navigation, focus changes, submission events | TBD |  | 7.3 | 2026-08-11 | 2026-08-13 |  |  | Not Started
7.7 | Post-Exam Score Analytics | Per-student and per-question performance breakdown | TBD |  | 7.4 | 2026-08-14 | 2026-08-17 |  |  | Not Started
8.0 | Multi-Type Exam Builder |  |  |  | - |  |  |  |  | Not Started
8.5 | Per-Student Question Randomization | Randomize question order per student | BRIAN |  | 8.4 | 2026-07-28 | 2026-07-28 |  |  | Not Started
8.6 | Teacher Can Update Scores | Manual score override/adjustment after grading | TBD |  | 2.4 | 2026-08-24 | 2026-08-25 |  |  | Not Started
10.0 | Result & Incident Report Export |  |  |  | - |  |  |  |  | Not Started
10.1 | Per-Student Score Breakdown CSV Export | Full results sheet exported as CSV | TBD |  | 2.4 | 2026-08-25 | 2026-08-26 |  |  | Not Started
10.2 | Incident Report (Violations w/ Timestamps) | Lists all logged violations per session | TBD |  | 7.5 | 2026-08-26 | 2026-08-27 |  |  | Not Started
10.3 | Immediate Export Generation | Exports generate right after exam ends, no config needed | TBD |  | 10.2 | 2026-08-27 | 2026-08-28 |  |  | Not Started
11 | Guided Installation & Deployment Package |  |  |  | - |  |  |  |  | Not Started
11.1 | Installer Setup Wizard (Teacher & Student) | Guided install flow for both user types | TBD |  | M1 | 2026-08-25 | 2026-08-28 |  |  | Not Started
11.2 | Auto-Configure Dependencies & Components | Installer sets up required components automatically | TBD |  | 11.1 | 2026-08-26 | 2026-08-28 |  |  | Not Started
11.3 | Dependency Verification & Setup Instructions | Checks for missing language runtimes, shows guidance | TBD |  | 11.2 | 2026-08-26 | 2026-08-28 |  |  | Not Started
11.4 | Future Update Deployment Support | Installer releases support reconfiguration-free updates | TBD |  | 11.3 | 2026-08-26 | 2026-08-28 |  |  | Not Started
12.0 | Nice-to-Have Features |  |  |  | - |  |  |  |  | Not Started
12.1 | USB & External Port Restriction | Disable external ports during active exam, auto-restore after | TBD |  | 1.5 | 2026-08-28 | 2026-08-31 |  |  | Not Started
12.2 | Hidden Process Detection | Flag disguised or concealed background processes | TBD |  | 1.6 | 2026-08-28 | 2026-08-31 |  |  | Not Started
13.0 | Testing & Quality Assurance |  |  |  | - |  |  |  |  | Not Started
13.1 | Functional Testing (All Modules) | End-to-end testing of lockdown, compiler, builder, dashboards | TBD |  | 1.8, 5.3, 7.7, 8.6, 10.3, 11.4, 12.2, 12.3 | 2026-08-31 | 2026-09-03 |  |  | Not Started
13.2 | Security & Lockdown Penetration Testing | Attempt bypasses of the exam lockdown system | TBD |  | 13.1 | 2026-09-01 | 2026-09-03 |  |  | Not Started
13.3 | User Acceptance Testing (UAT) | Stakeholder walkthrough and sign-off | TBD |  | 13.2 | 2026-09-01 | 2026-09-03 |  |  | Not Started
14.0 | Deployment |  |  |  | - |  |  |  |  | Not Started
14.1 | Production Hosting Setup | Provision production Supabase project and build distribution | TBD |  | 13.3 | 2026-09-03 | 2026-09-04 |  |  | Not Started
14.2 | Go-Live Deployment | Ship final build to production | TBD |  | 14.1 | 2026-09-03 | 2026-09-04 |  |  | Not Started
M2 | 100% MILESTONE DEFENSE | Group milestone checkpoint, not an individual task | ALL |  | - | 2026-07-21 | 2026-09-04 |  |  | Not Started

## Legend & Notes
WBS Legend
Level 1 - Module/Phase | Top-level grouping, e.g. User Management Module (CRUD)
Level 2 - Task | A core function within the module, e.g. List Users, Create User
Level 3 - Subtask | A step needed to complete the task, e.g. Build Table, Hard Delete
Level 4 - Subtask of Subtask | Further breakdown, e.g. Export to CSV / Excel / PDF
Notes for students:
- Date Started (Actual) / Date Finished (Actual) are left blank on purpose - fill these in as work actually happens, to compare against the Planned columns.
- Duration (days) = number of business days (Mon-Fri) the row takes; for Module/Task/Subtask group rows it is the span covering all of their child rows.
- Predecessor(s) lists the WBS Code(s) of row(s) that must finish first. A '-' means the row has no predecessor (it can start at project kickoff).
- Start Date / Deadline are auto-generated example dates based on business days (Mon-Fri) and task dependencies.
- Parent rows (Module/Task/Subtask groups) show a rolled-up date range covering all of their child rows.
- Dev 1 & Dev 2 work in parallel on the User Management module (frontend vs. backend split).
- Dev 3 owns the Faculty module solo; Dev 4 owns the News module solo - showing modules can run in parallel across devs.
- Within a single module, subtasks run sequentially (e.g., a form must be built before it can be validated, before it can save to DB).
- Testing depends on ALL THREE modules being finished (it waits for the latest of the three Delete/Soft Delete subtasks).
- Deployment depends on UAT sign-off being complete.
- This is a teaching example; adjust Dev count, durations, and start date to fit your own class project.